## Timeline
|  | 2015-05-01 | [20 empty] | 2015-06-01
Phase 1 Theme Design & Static Pages |  | Week1 | [6 empty] | Week2 | [6 empty] | Week3 | [6 empty] | Week4 | [6 empty] | Week5
No. | Activity | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | ออกแบบและนำเสนอ Theme Design | bar: Week1 11 to Week2 18
2 | Approve Theme Design | bar: Week2 19 to Week2 20
3 | จัดหน้า Static Pages (ดูเอกสาร Static Pages) | bar: Week2 19 to Week3 30
4 | นำเสนอ Site Map และ Approve Menu Links | bar: Week3 31 to Week4 2
5 | จัดรูปภาพลง Static Pages และ Approve by owner | bar: Week3 31 to Week4 7
6 | ปรับปรุงและแก้ไข เพิ่มเติม | bar: Week5 8 to Week5 14
|  | 2015-06-01 | [15 empty] | 2015-07-01
Phase 2 Subsystem Prepare |  | Week1 11: Week6; Week2 18: Week7; Week3 25: Week8; Week4 1: Week9; Week5 8: Week10
| Activity | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | เก็บความต้องการ Subsystem (ดูเอกสาร ระบบย่อย) | bar: Week6 15 to Week7 28
2 | ออกแบบจัดทำเอกสารระบบพอสังเขป Flow Chart,UML,ERD | bar: Week7 22 to Week8 4
3 | ออกแบบ Entrity, Data Dictionary,Table และ DB Relation | bar: Week8 1 to Week9 7
4 | เก็บความต้องการ Webboard สิทธิ์การเข้าถึงต่างๆ | bar: Week9 6 to Week9 12
5 | จัดทำ Webboard และ Approve by owner | bar: Week8 29 to Week9 12
6 | ปรับปรุงและแก้ไข เพิ่มเติม | bar: Week10 13 to Week10 19
|  | 2015-07-01 | [11 empty] | 2015-08-01
Phase 3 Subystem Setup |  | Week6 15: Week6; Week7 22: Week7; Week8 29: Week8; Week9 6: Week9; Week10 13: Week10
| Activity | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Create and Import DB | bar: Week6 20 to Week7 2
2 | Coding and Testing Energy Express | bar: Week6 20 to Week8 8
3 | Coding and Testing Paper / Lesson Learned | bar: Week6 20 to Week9 11
4 | Coding and Testing Application Download | bar: Week6 26 to Week9 16
5 | Coding and Testing Avaliable Course and Workshop | bar: Week6 26 to Week9 16
6 | Coding and Testing Job Classifiled | bar: Week8 3 to Week10 23
7 | Coding and Testing News and Update | bar: Week8 3 to Week10 23
8 | Coding and Testing Oil market Analysis / Oil Price | bar: Week8 3 to Week8 9
9 | Coding and Testing Stock Price | bar: Week10 17 to Week10 23
10 | Coding and Testing Login Portal and config Permission | bar: Week10 17 to Week10 23
|  | 2015-08-01 | [7 empty] | 2015-09-01
Phase 4 ปรับปรุงและแก้ไขเพิ่มเติม |  | Week6 20: Week11; Week7 27: Week12; Week8 3: Week13; Week9 10: Week14; Week10 17: Week15
| Activity | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
1 | ปรับปรุงแก้ไขเนื้อหา Static Page (if Owner Required) | bar: Week11 24 to Week12 6
2 | Test Subsystm By Owner | bar: Week12 31 to Week13 12
3 | ปรับปรุงแก้ไขเนื้อหา Subsystem Page (if Owner Required) | bar: Week13 9 to Week14 15
4 | Launch Website to Owner Hosting and Testing | bar: Week13 10 to Week14 16
5 | Setup Google Analytics | bar: Week14 14 to Week14 16
6 | Key Users Traning | bar: Week14 14 to Week15 27

## Static Pages
No. | Static Page & Theme | ราคา/บาท | รวม/บาท
1 | Frontend Theme
| โครงสร้างหลักและสัดส่วนของเว็บ | 2500
| ออกแบบและจัดวาง Menu, Header, Body, Footer | 3500
| Legal Font and Theme | 12000
| รวม |  | 18000
2 | Corporate Profile
| Company History | 2500
| Vision & Mission | 2500
| Business Overview | 2500
| Organization Chart | 2500
| Code of Conduct | 2500
| รวม |  | 12500
3 | Corporate Governance
| Safety | 2500
| QA & QC | 2500
| To Be Advised. | 2500
| To Be Advised. | 2500
| รวม |  | 10000
4 | Services
| Our Core Business | 2500
| Operation Excellence | 2500
| Partnership | 2500
| รวม |  | 7500
5 | Knowlendge Mangement
| KM Forum | 2500
| Press Center | 2500
| รวม |  | 5000
6 | Training & Conference
| Technical Training | 2500
| Availible Course | 2500
| Conference & Workshop | 2500
| To Be Advised. | 2500
| รวม |  | 10000
7 | PTTES PEOPLE
| HR Strategy | 2500
| PTTES SPIRIT | 2500
| HR Management System | 2500
| HR Development | 2500
| Employee Engagement | 2500
| Reward System | 2500
| Jop Opportunity | 2500
| Internship | 2500
| รวม |  | 20000
7 | Contact Us
| Public | 2500
| Marketing Contact | 2500
| Customer Login Portal | 2500
| รวม |  | 7500
| Total |  | 90500

## Sub System
No. | Sub System | ราคา/บาท | รวม/บาท
1 | Energy Express
| Database Design | 2000
| Backend for Energy Express | 5000
| Frontend and Register form | 2500
| รวม |  | 9500
2 | KM Forum
| Weboard Installation | 5000
| CSS Modify and Tuning | 2500
| Right and Permission Configulation | 1500
| Toppic Configulation | 2000
| Test and Run | 2000
| รวม |  | 13000
3 | Paper / Lesson Learned
| Database Design | 2000
| Backend for Paper / Lesson Learned | 5000
| Subscribe / Unscripbe Function | 2500
| Frontend Paper / Lesson Learned | 3500
| รวม |  | 13000
4 | Application Download
| DB and Workspace Design | 2000
| Backend for Application Download | 5000
| Frontend Application List | 3500
| รวม |  | 10500
5 | Avaliable Course
| Database Design | 2000
| Backend for Avaliable Course | 5000
| Frontend Avaliable Course list | 3500
| Frontend Register Form | 3500
| รวม |  | 14000
6 | Avaliable Workshop
| Database Design | 2000
| Backend for Avaliable Workshop | 5000
| Frontend Avaliable Workshop list | 3500
| Frontend Register Form | 3500
| รวม |  | 14000
7 | Job Classifiled
| Database Design | 2000
| Backend for Update Job Required | 5000
| Frontend Avaliable Job Descliption list | 3500
| รวม |  | 10500
8 | News and Update
| Database Design | 2000
| Backend for News and Update | 5000
| Frontend AvaliableNews and Update list | 3500
| รวม |  | 10500
9 | Oil market Analysis / Oil Price
| Database Design | 2000
| Backend for Oil market Analysis / Oil Price | 5000
| Frontend Oil market Analysis / Oil Price | 3500
| รวม |  | 10500
10 | Stock Price
| Database Design | 2000
| Backend for Stock Price | 3500
| Frontend Stock Price | 3500
| รวม |  | 9000
11 | PTT OpEx Portal
| Page Arrange and Design | 2500
| รวม |  | 2500
12 | Count Number
| Google Analytics Prepare | 2500
| Google Analytics Setup | 2500
| Google Analytics Report | 3000
| รวม |  | 8000
13 | Customer Login Portal and Backend Login Poltal
| Database Design | 3500
| Permisstion Design | 2000
| Backend for Permisstion Configulation | 5000
| Helpdesk Service | 3500
| Online Report | 3500
| TSA Utilization | 3500
| รวม |  | 21000
| Total |  | 146000